## Sprint Backlog
User Story | Task Id | Task Description
US001 | T00002 | Identify open source technologies for prototype development.
| T00003 | Draft high level technical design for complete application.
| T00004 | Understand fda food datasets and API usage
| T00005 | Setup environment and Continuous integration server for project. (Jenkins)
| T00006 | Design frontend web pages
| T00007 | Go through design web interfaces with Product Owner
| T00008 | Design content in accordance to user requirements.
| T00009 | Sprint planning meeting preparation activites. (This is added as task to track time)
US002 | T00010 | Develop code for home page and search functionality.
| T00011 | Write automated test cases for search
| T00012 | Peer code review with other team members.
| T00013 | Usability testing with end user
US003 | T00014 | Develop code for product information search functionality.
| T00015 | Write automated test cases for search
| T00016 | Peer code review with other team members.
| T00017 | Usability testing with end user
US007 | T00018 | Develop code to display search content in user friendly manner ( should be inline with finalized design)
| T00019 | Write test cases for search content.
| T00020 | Peer code review with other team members.
| T00021 | Usability testing with end user
US008 | T00022 | Develop code to share searched content with other users.
| T00023 | Write test case for this feature.
| T00024 | Peer code review with other team members.
| T00025 | Usability testing with end user
US009 | T00026 | Develop code for help and faq section
| T00027 | Get content from content writer for faq
| T00028 | Peer code review with other team members.
| T00029 | Usability testing with end user
US010 | T00030 | Develop code for feedback form
| T00031 | Write test cases for feedback form
| T00032 | Peer code review with other team members.
| T00033 | Usability testing with end user
US004 | T00034 | Develop code for search functionality.
| T00035 | Write automated test cases for search
| T00036 | Peer code review with other team members.
| T00037 | Usability testing with end user
US005 | T00038 | Develop code for search functionality.
| T00039 | Write automated test cases for search
| T00040 | Peer code review with other team members.
| T00041 | Usability testing with end user
US006 | T00042 | Develop code for search functionality.
| T00043 | Write automated test cases for search
| T00044 | Peer code review with other team members.
| T00045 | Usability testing with end user
US011 | T00046 | Develop code for fda news link
| T00047 | write test case
| T00048 | Peer code review with other team members.
| T00049 | Usability testing with end user
US012 | T00050 | Develop code for food recall reports by classification.
| T00051 | Write test cases.
| T00052 | Peer code review with other team members.
| T00053 | Usability testing with end user