## Sprint Backlog
User Story | Task Id | Task Description | Sprint Number | Assigned Person | Start Date | End Date | Status
US001 | T00002 | Identify open source technologies for prototype development. | 1 | Balaji | 2015-06-18 | 2015-06-23 | Closed
| T00003 | Draft high level technical design for complete application. | 1 | Balaji | 2015-06-18 | 2015-06-23 | Closed
| T00004 | Understand fda food datasets and API usage | 1 | Igor | 2015-06-18 | 2015-06-23 | Closed
| T00005 | Setup environment and Continuous integration server for project. (Jenkins) | 1 | Jesse | 2015-06-18 | 2015-06-23 | Closed
| T00006 | Design frontend web pages | 1 | Igor | 2015-06-18 | 2015-06-23 | Closed
| T00007 | Go through design web interfaces with Product Owner | 1 | Igor | 2015-06-18 | 2015-06-23 | Closed
| T00008 | Design content in accordance to user requirements. | 1 | Igor | 2015-06-18 | 2015-06-23 | Closed
| T00009 | Sprint planning meeting preparation activites. (This is added as task to track time) | 1 | Jeet | 2015-06-18 | 2015-06-23 | Closed
US002 | T00010 | Develop code for home page and search functionality. | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00011 | Write automated test cases for search | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
| T00012 | Peer code review with other team members. | 1 | Balaji | 2015-06-23 | 2015-06-24 | Closed
| T00013 | Usability testing with end user | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
US003 | T00014 | Develop code for product information search functionality. | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00015 | Write automated test cases for search | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
| T00016 | Peer code review with other team members. | 1 | Balaji | 2015-06-23 | 2015-06-24 | Closed
| T00017 | Usability testing with end user | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
US007 | T00018 | Develop code to display search content in user friendly manner ( should be inline with finalized design) | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00019 | Write test cases for search content. | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
| T00020 | Peer code review with other team members. | 1 | Balaji | 2015-06-23 | 2015-06-24 | Closed
| T00021 | Usability testing with end user | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
US008 | T00022 | Develop code to share searched content with other users. | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00023 | Write test case for this feature. | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
| T00024 | Peer code review with other team members. | 1 | Balaji | 2015-06-23 | 2015-06-24 | Closed
| T00025 | Usability testing with end user | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
US009 | T00026 | Develop code for help and faq section | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00027 | Get content from content writer for faq | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00028 | Peer code review with other team members. | 1 | Balaji | 2015-06-23 | 2015-06-24 | Closed
| T00029 | Usability testing with end user | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
US010 | T00030 | Develop code for feedback form | 1 | Jesse | 2015-06-23 | 2015-06-24 | Closed
| T00031 | Write test cases for feedback form | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
| T00032 | Peer code review with other team members. | 1 | Balaji | 2015-06-23 | 2015-06-24 | Closed
| T00033 | Usability testing with end user | 1 | Igor | 2015-06-23 | 2015-06-24 | Closed
US004 | T00034 | Develop code for search functionality. | 2 | Jesse | 2015-06-25 | 2015-06-29 | Closed
| T00035 | Write automated test cases for search | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
| T00036 | Peer code review with other team members. | 2 | Balaji | 2015-06-25 | 2015-06-29 | Closed
| T00037 | Usability testing with end user | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
US005 | T00038 | Develop code for search functionality. | 2 | Jesse | 2015-06-25 | 2015-06-29 | Closed
| T00039 | Write automated test cases for search | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
| T00040 | Peer code review with other team members. | 2 | Balaji | 2015-06-25 | 2015-06-29 | Closed
| T00041 | Usability testing with end user | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
US006 | T00042 | Develop code for search functionality. | 2 | Jesse | 2015-06-25 | 2015-06-29 | Closed
| T00043 | Write automated test cases for search | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
| T00044 | Peer code review with other team members. | 2 | Balaji | 2015-06-25 | 2015-06-29 | Closed
| T00045 | Usability testing with end user | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
US011 | T00046 | Develop code for fda news link | 2 | Jesse | 2015-06-25 | 2015-06-29 | Closed
| T00047 | write test case | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
| T00048 | Peer code review with other team members. | 2 | Balaji | 2015-06-25 | 2015-06-29 | Closed
| T00049 | Usability testing with end user | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
US012 | T00050 | Develop code for food recall reports by classification. | 2 | Jesse | 2015-06-25 | 2015-06-29 | Closed
| T00051 | Write test cases. | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
| T00052 | Peer code review with other team members. | 2 | Balaji | 2015-06-25 | 2015-06-29 | Closed
| T00053 | Usability testing with end user | 2 | Igor | 2015-06-25 | 2015-06-29 | Closed
US013 | T00054 | Develop code for food recall reports by classification. | 2 | Jesse | 2015-06-30 | 2015-07-01 | Closed
| T00055 | Write test cases. | 2 | Igor | 2015-06-30 | 2015-07-01 | Closed
| T00056 | Peer code review with other team members. | 2 | Balaji | 2015-06-30 | 2015-07-01 | Closed
| T00057 | Usability testing with end user | 2 | Igor | 2015-06-30 | 2015-07-01 | Closed
US014 | T00058 | Setup google forms | 2 | Jesse | 2015-06-30 | 2015-07-01 | Closed
| T00059 | Embed form on site. | 2 | Jesse | 2015-06-30 | 2015-07-01 | Closed
| T00060 | Test and review code. | 2 | Igor | 2015-06-30 | 2015-07-01 | Closed